|  | Educational & practice grant timeline | Niedfelt Nursing Research Center |
| --- | --- | --- |
| PI: |  | Grant: |  |
| Project Title: |  |
| Weeks Prior to Deadline | PI Deadline | PI Tasks |
| 6 weeks |  | Meet with Assistant Dean to discuss research project and % effort |
| 6 Weeks |  | Submit Signed Assistant-Associate Dean Approval Form to NNRC |
| 6 weeks |  | Meet with the Associate Dean* - Review initial aims and direction, viability and impact on CON, and discuss all aspects of financial items / expenses |
| 6 weeks |  | Meet with NNRC Administrator - Review timeline & grant planning form (co-investigators; consultants; subcontracts; RefWorks; etc.) |
| 6 weeks |  | Are there any participants not at UNMC on the grant? If yes, a Subcontract will need to be initiated. Contact the NNRC. |
| 5 weeks |  | Meet with NNRC staff to develop initial budget and discuss subcontracts |
| 4 weeks |  | NNRC staff to schedule mock review |
| 4 weeks |  | PI to provide NNRC staff with draft proposal, any other pertinent documents for mock review |
| 4 weeks |  | Start working on Biosketch. What format does the Agency require? |
| 3 weeks |  | Mock Review |
| 3 weeks |  | Submit proposal draft for 2nd round of reviews to designated individuals |
| 3 weeks |  | Meet with NNRC staff to finalize budget. Send final budget to the Associate Dean* for final review |
| 3 weeks |  | NNRC staff to follow up on all pending biosketches & letters of support |
| 2 weeks |  | Send to UNMC Editor for review (this is a fee based service and optional) |
| 2 weeks |  | Meet with NNRC staff to review pending items |
| 2 weeks |  | Provide NNRC with proposal to allow time for editing and formatting |
| 2 weeks |  | NNRC staff sends the budget to the Associate Dean* |
| 2 weeks |  | Sign internal budget forms |
| 1 week |  | Complete proposal due to SPAdmin: NNRC to upload all required documents |
| 1 week |  | PI to review all documents for accuracy and approval |
| 3 days |  | Grant submitted to funding agency |
| Due Date |  | Grant Deadline |

* Associate Dean for Academic Programs OR Associate Dean for Transformational Practice and Partnerships